## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | DateEnd
1 | Nguyễn Văn Bảo Nguyên | baonguyen010599 | Product Owner,Dev | 2022-04-03
2 | Phan Nguyễn Minh Phát | phannguyenminhphat1 | Dev | 2022-04-03
3 | Phan Như Hải Lưu | luuphan | Dev | 2022-04-03
4 | Võ Tấn Lộc | TanLoc1604 | Dev | 2022-04-03
5 | Trương Anh Kiệt | Anh0kiet | Dev | 2022-04-03

## ProductBacklog
WEBSITE THI TRẮC NGHIỆM - PRODUCT BACKLOG
Story ID | Story Name | Point
76
Actor: Học sinh
1 | Đăng nhập | 2
2 | Thi | 4
3 | Nộp bài | 6
4 | Xem điểm | 6
5 | Xem đáp án | 4
6 | Xem danh sách các môn đã thi | 6
Actor: Giáo viên
1 | Đăng nhập | 2
2 | Nhập câu hỏi | 6
3 | Nhập đáp án | 4
4 | Tạo đề thi | 6
5 | Xem danh sách các đề thi theo môn của giáo viên giảng dạy | 2
6 | Xem kết quả thi của học sinh
Actor: Quản trị viên
1 | Đăng nhập | 2
2 | Quản lý lớp học ( thêm, xóa , sửa lớp ) | 2
3 | Quản lý môn học (thêm, xóa, sửa môn học) | 6
4 | Quản lý giáo viên (thêm, xóa, sửa giáo viên) | 6
5 | Quản lý giảng dạy ( thêm , xóa , sửa ) - quá trình giảng dạy | 6
6 | Quản lý học sinh ( thêm, xóa, sửa hs) | 6
7 | Nhập thời gian thi

## SprintBacklog
E-COMMERCE PROJECT - SPRINT BACKLOG
Story ID | Story Name | Points | Name of Dev | Start Date | End Date | Act Start Date | Act End Date | Act Point | Notes
20
Sprint 1
1 | Đăng nhập | 2 | TanLoc1604 | 2022-04-03 | 2022-04-10
2 | Trang chủ | 4 | phannguyenminhphat1 | 2022-04-03 | 2022-04-10
3 | Thi | 4 | baonguyen010599 | 2022-04-03 | 2022-04-10
4 | Nộp bài | 4 | luuphan | 2022-04-03 | 2022-04-10
5 | Tra cứu thông tin | 2 | Anh0kiet | 2022-04-03 | 2022-04-10
6 | Xem kết quả | 4 | phannguyenminhphat1 | 2022-04-03 | 2022-04-10
Sprint 2